## Worksheet
Task | Month
T1.1 | 1-27 | Characterise design and governance aspects of European W-for-W PES.
T1.2 | 22-36 | Identify Best Practice in PES design and governance, using Case Studies.
T1.3 | 31-48 | Training and guidance for ‘Design and Governance’ chapter of ‘User Manual’.
Milestones
M1.1 | 15 | STSM (A), exploring potential investors’ perceptions of what would be needed to attract them to purchase credits, and interest in providing finance.
M1.2 | 24 | STSM (B), exploring motivations and barriers of other potential PES participants (e.g. farmers, water utilities, landowners and the general public).
M1.3 | 33 | STSM (C), engaging with policy-makers on best governance of new schemes + explore potential for citizen science to monitor completed PES schemes.
M1.4 | 39 | Training School ‘PES design and governance’, including participatory approaches to stakeholder interaction at river basin level.
Deliverables
D1.1 | 18 | Report on investors’ perceptions
D1.2 | 28 | Report on motivations of potential PES participants and barriers.
D1.3 | 36 | Report on governance and engaging with policy-makers.
D1.4 | 39 | ‘Design and Governance’ chapter for ‘User Manual’