## Worksheet
Task | Month
T4.1 | 1-3 |  | Agree Dissemination and Exploitation Plan (M2).
T4.2 | 1-48 |  | Design, create, promote, extend and maintain the PESFOR-W web hub.
T4.3 | 1-15 |  | Expand the network of countries involved in assisting collection of information on existing PES pilots, projects and best practice.
T4.4 | 1-9 |  | Conduct EU online web survey to gather information/opinions on W-for-W PES.
T4.5 | 10-45 |  | Collect key details, including financial and socioeconomic information for W-for-W PES fact sheets for existing and new Case Studies.
T4.6 | 24-48 |  | Synthesise and edit Best Practice in the ‘User Manual: Smarter Guidance on Woodlands-for-Water PES’; translated into 6 European languages.
T4.7 | 24-48 |  | Organise/deliver Final Conference (Month 45) by Conference Committee.
Milestones
M4.1 | 6 | Spatial hub operational.
M4.2 | 10 | Launch online web survey.
M4.3 | 21 | STSM (k) collecting key data, including financial and socioeconomic information, on W-for-W PES schemes for Case Study fact sheets.
M4.4 | 27 | Existing Case Studies are all on Spatial Repository on PESFOR-W website.
M4.5 | 28 | Establish skills database on ‘European PES Expertise’.
M4.6 | 29 | STSM(l) on best marketing and communication practices for PES.
M4.7 | 45 | Final Conference takes place.
M4.8 | 45 | 4th Training School, on applying the User Manual.
Deliverables
D4.1 | 6 | PESFOR-W website.
D4.2 | 27 | Publication of factsheets on existing Case Studies on W-for-W PES.
D4.3 | 33 | Report on ‘Communicating the PES “Wow factor’” (- ‘User Manual’ Chapter).
D4.4 | 39 | Publication of Final Case Study synthesis chapter for ‘User Manual’.
D4.5 | 42 | Publish ‘User Manual: Smarter guidance on W-for-W PES schemes’
D4.6 | 1-48 | Other knowledge exchange activities (e.g. via social media and press).
D4.7 | 48 | Final Conference published proceedings and Final Project Report.