## Worksheet
Risk | Impact | Mitigation
Limited involvement of researchers in the Action. | Too few researchers involved in the Working Groups making the goals difficult to achieve. | Ensure a broad and balanced membership and work plan. Links with international academic bodies will be used to attract new Action Members.
Limited engagement by stakeholders. | The Action will be restricted to academia and not find entry into EU-wide or contractor-led level. | There are established contacts to a wide range of stakeholders from EU- to local scale. Thus, only sporadic drop-outs are expected. Involvement of higher level, politically powerful, heritage managers will be sought.
Disengagement of participants and a lack of coordination. | Delays/lack of Action participants. | SAGA’s management structures (Section 3.2) are a guarantee for keeping the Action on track and monitoring its progress. SAGA will promote the use of social media to keep the Action current in people's minds, including publicising others' related work. SAGA is really going to be pumping engagement.
Limited dissemination. | Achievements will not contribute to the community / future ofthe discipline. | Robust dissemination will be guaranteed by activities such as: mentorship schemes (‘Access to Experts’); Training Schools; website and online resources; teleconferencing). The focus on training and involving the next generation of scholars and stakeholders (ECIs and high profile experts employed by the industry and public organisations) through SAGA events and STSMs will be crucial to ensure the longevity of the outcomes.
Failure to sustain the community established during the Action. | Interest will fall apart and there will be a loss of momentum towards the particular research topic. | SAGA’s partners represent a lively research community and there is an increasing interest to the topic. The databases, training material, library of geophysical / soil signatures will be sustained in the main servers of SAGA and will continue to feed the next generation of practitioners. SAGA will promote engagement in longer term cooperation with other funding sources, or will register a body, which will represent the network created.