## Worksheet
Description of risks | Risk-mitigation measures
R1: The new instruments, workflows and measures are not or only slowly accepted by the communityLikelihood: Low | Development of the infrastructure according to the users’ needs and preferences, based on user surveys and continuous feedback.TA(s) involved: TA5, TA6
R2: The development and international agreement on (new) standards is not fast enough and the NFDI4Chem consortium is missing basic models on how to generate interfaces, report, export, and transfer dataLikelihood: medium | Solutions to the given risks are described in TA4 and TA6 (Chamanara et al. 2019). NFDI4Chem starts with reasonable models that are not agreed on internationally but can be extended in a flexible manner. Adaptation to international agreements in a second step.TA(s) involved: TA4, TA6
R3: Inadequate interfaces to related NFDI services could affect the project.Likelihood: low | The interfaces will be part of cross-cutting topics and discussions.TA(s) involved: TA6
R4: Manufacturers of devices do not agree on common open interfaces and open formats to facilitate the data transfer and data readability. Likelihood: high | Data transfer from devices is realized via three alternative strategies. If the manufacturers will not collaborate, the NFDI4Chem will focus on the strategies which work without the manufacturers’ commitment with respect to data availability (T 2.1.1. and T 2.1.2) and conversion (T4.3.2).TA(s) involved: TA2, TA4
R5: The implemented data viewer(s) will not cover the whole range of possible data formats of the community: The variety of data formats and also currently missing standards (allowing a limitation of output files) may complicate the process.Likelihood: medium | TA2 will focus on the most important file formats for each analysis type and experimental setup (surveys TA5). For uncommon file types and proprietary files, a common strategy towards standardised file formats will be developed in TA4.TA(s) involved: TA2, TA3, TA4
R6: The installation of the required AAI for operation of the ELN as a service is delayedLikelihood: medium | A user access model with limited authorisation functions will be developed to serve as an intermediate solution to be replaced by the NFDI overarching AAI as soon as available.TA(s) involved:TA6
R7: Security risks and data leakage for the decentrally installed ELNs and ELN as a ServiceLikelihood: low | The ELN software will undergo regular security checks as part of the CI process and penetration tests. KIT-SCC will provide guidelines for a secure runtime environment.ELN as a service is hosted in a professionally operated data centre at KIT-SCC. It benefits from a sophisticated security architecture with firewalls, intrusion detection systems and virus scanners maintained by experienced administrators.TA(s) involved: TA2
R8: The productive operation of the ELN as a service is not possible because the requirements for the availability of the service are too high. Likelihood: low | The operation takes place in a professional data centre with great experience in the provision of redundantly designed services to achieve high reliability. In addition, the operation can be mirrored in another data centre (FIZ) if required.TA(s) involved: TA2