## Worksheet
Description of risks | Risk-mitigation measures
R1: The finalisation of community standards regarding minimal information standards takes too long.Likelihood: Low | TA3 provides for an iterative approach in which also partial results can be implemented.TA(s) involved: TA3, TA2, TA4
R2: The implementation of API and minimal information standards are impeded by missing resources of the repository operators.Likelihood: medium | In addition to the personnel resources earmarked for this purpose for the repository operators, KIT-SCC and FIZ provide additional development capacities.TA(s) involved: TA3
R3: Compliance with CTS certification requirements is proving difficult for repositories.Likelihood: medium | TA3 supports the repositories with digital long-term archiving services and the provision of suitable hosting environments, in particular to address aspects of sustainable and reliable operation.TA(s) involved: TA3
R4: Important datasets or databases in the field of chemistry are no longer maintained by their current hosts.Likelihood: high | TA3 has earmarked resources for the transfer of data sets and databases to appropriate repositories in order to preserve them for research.TA(s) involved: TA1, TA5
R5: Security risks and leakage of unpublished dataLikelihood: medium | TA3 will assess the technical architecture of all selected repositories (cf. task 3.2.1) and support repository operators to improve the operational fitness of their services, including security aspects. Additionally, repositories are upgraded to be easily transferable to more secure hosting environments where necessary.TA(s) involved: TA3