## Worksheet
WP Nr. | Task sharing | workload (PM)
1 | The TIB carries out the requirements analysis using different methods and involving the various external partners and experts. | TIB: 9
2 | The technical conception of the plugins and transfer of the user stories into implementation tasks is carried out jointly by TIB and WWU. The TIB prepares the basic development and test infrastructure and begins as early as possible with the preparatory testing of the basic software as well as related projects and external communication. | TIB: 3WWU: 2
3 | The WWU is in charge of developing the geoplugin, the TIB the citation plugin. Both institutions are involved in the development of the other plugin to a certain degree in order to ensure a sustainable and effective development and to use synergy effects. The TIB supports the testing of releases by another project staff member and is also responsible for troubleshooting and, if necessary, further development of the plugins during testing after the end of the WWU sub-project, as well as for the releases. | TIB: 7WWU: 6
4 | The TIB and the WWU jointly realise the shared code base for overlapping export functions of the plugins and the porting of the plugins to other potentially wide-reaching publication platforms. The WWU develops an implementation concept and a prototype for a cross-journal geodata-based search portal with simultaneous testing of harvesting variants. | TIB: 1WWU: 3
5 | The TIB is responsible for the sustainable dissemination and communication of the project results in various forms of publication, especially in documentation, scientific publications and project reports, as well as in events, especially webinars and the final workshop. The WWU supports the writing of publications and participates in events. WWU and TIB jointly support the partner journals including on-site meetings. | TIB: 10WWU: 1
Total: 42