## Worksheet
Deliv. no. | Deliverable name | WP no. | Lead Part. | Type | Diss. Level | Delivery date
D1.1 | Scoping review of scientific virtues for training | 1 | 3 - MEFST | OTHER | PU | 18
D1.2 | Report on the results from the stakeholder focus groups | 1 | 3 - MEFST | R | PU | 12
D1.3 | Report on results from the Delphi consultation process | 1 | 3 - MEFST | R | PU | 18
D2.1 | Report on the results of the ERI literature and practices review | 2 | 2 - KUL | R | PU | 12
D2.2 | Report on the results of the stakeholder consultation | 2 | 2 - KUL | R | CO | 12
D2.3 | List of priorities and dissemination strategies for ERI training programmes in Europe | 2 | 2 - KUL | R | PU | 18
D3.1 | First draft of the face-to-face train-the-trainer programme | 3 | 6 - UiO | DEM | CO | 14
D3.2 | Report on the experiences of piloting the face-to-face train-the-trainer programme | 3 | 6 - UiO | R | CO | 20
D3.3 | The face-to-face train-the-trainer programme | 3 | 6 - UiO | DEM | PU | 23
D4.2 | Delivery of the first educational videos on a dedicated YouTube channel | 4 | 4 - OeAWI | DEC | PU | 18
D4.1 | Delivery of first MOOC courses for VIRT2UE toolbox | 4 | 4 - OeAWI | DEC | PU | 20
D4.2 | 7 YouTube videos | 4 | 4 - OeAWI | DEC | PU | 24
D4.3 | Toolbox for trainers | 4 | 4 - OeAWI | DEC | PU | 24
D4.4 | Massive Open Online Course (MOOC) – 6 courses | 4 | 4 - OeAWI | DEC | PU | 34
D5.1 | List of ERI teachers | 5 | 5 - EUREC | R | PU | 12
D5.2 | Report on face-to-face training-the-trainer programmes (all countries) and implementation plan | 5 | 5 - EUREC | R | PU | 20
D5.3 | Dissemination strategy for the programme | 5 | 5 -EUREC | R | PU | 24
D5.4 | Capacity building road map | 5 | 5 -EUREC | R | PU | 28
D6.1 | The pilot version of the e-learning platform is online | 6 | 1 - VUmc | DEC | PU | 6
D6.2 | Report on findings of the pilot evaluation | 6 | 1 - VUmc | R | PU | 12
D6.3 | Version 2.0 of the e-learning platform is available | 6 | 1 - VUmc | DEC | PU | 24
D6.4 | Plan for future platform development | 6 | 1 - VUmc | R | PU | 36
D7.1 | Project management and quality assurance plan | 7 | 1 - VUmc | R | PU | 2
D7.2 | Documents providing templates and logo for a corporate and uniform look | 7 | 1 - VUmc | R | PU | 3
D7.3 | Data management plan | 7 | 1 - VUmc | ORDP | PU | 6
D7.4 | Report for the EC 1 | 7 | 1 - VUmc | R | PU | 18
D7.5 | Report for the EC 2 | 7 | 1 - VUmc | R | PU | 36