## Worksheet
Milestone number | Milestone name | Related WPs | Due date (in month) | Means of verification
M1.1 | Stakeholders’ feedback from focus groups collected and analysed | 1 | 12 | Report
M1.2 | Results from the scoping review of literature. | 1 | 18 | Report
M2.1 | Consensus meeting of experts on priorities for ERI training organised | 2 | 14 | Minutes sheet
M3.1 | Data from pilot phase collected and discussed with consortium members | 3 | 19 | Report
M3.2 | Train-the-trainer programme material online | 3 | 24 | Screens
M4.1 | First materials for online learning for trainers and researchers are available online | 4 | 6 | Website
M4.2 | MOOC and YouTube channel are online | 4 | 18 | Website
M4.3 | Toolbox for trainers is available online | 4 | 24 | Website
M5.1 | Database of ERI teachers | 5 | 20 | Launch
M5.2 | Face-to-face train-the-trainer programmes organised, covering all EU countries, Turkey, Norway and Switzerland | 5 | 30 | Training
M6.1 | The pilot version of the e-learning platform is available | 6 | 6 | Website
M6.2 | Version 2.0 of the e-learning platform is available | 6 | 24 | Website
M6.3 | Over 50,000 users across more than 10 European countries have used the e-learning platform | 6 | 36 | User statistics of the platform
M7.1 | Kick off meeting | 7 | 2 | Minutes sheet