## Worksheet
Project year and month |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
|  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48
T1.1 | Scientific coordination | bar: Year 1 3 to Year 4 48
T1.2 | Administrative coordination | bar: Year 1 3 to Year 4 48
T1.3 | Financial coordination | bar: Year 1 3 to Year 4 48
T2.1 | Preparation of the stakeholder consultation | bar: Year 1 3
T2.2 | Pilot: face-to-face focus groups withs takeholders | bar: Year 1 6
T2.3 | Defining the boundaries of the data to be collected | bar: Year 1 6 to Year 1 12
T2.4 | Scale -up: Online focus groups with stakeholders | bar: Year 1 9 to Year 2 15
T2.5 | Assessing the acceptability of the online platform | bar: Year 2 18 to Year 4 48
T3.1 | Preparation of data-collection on normative documents | bar: Year 1 3 to Year 1 6
T3.2 | Pilot collection of data on normative documents | bar: Year 1 9 to Year 1 12
T3.3 | Scale up: Collecting normative documents in all EU countries | bar: Year 2 15 to Year 3 33
T3.4 | Analysis of the normative documents | bar: Year 1 12 to Year 3 30
T3.5 | Testing, updating and optimizing online platform | bar: Year 2 18 to Year 4 48
T4.1 | Preparation of data collection on resources | bar: Year 1 3 to Year 1 6
T4.2 | Pilot collection of data on resources | bar: Year 1 9 to Year 1 12
T4.3 | Scale-up: Inventory database on resources for European countries | bar: Year 2 15 to Year 3 36
T4.4 | Testing, updating and optimizing the online platform | bar: Year 2 18 to Year 4 48
T5.1 | Preparation of data collection on cases | bar: Year 1 3 to Year 1 6
T5.2 | Pilot collection of data on cases | bar: Year 1 9 to Year 1 12
T5.3 | Scale up: Collecting and categorizing RE+RI cases | bar: Year 2 15 to Year 3 33
T5.4 | Identifying and applying appropriate case analysis methods and building RE+RI scenarios | bar: Year 2 15 to Year 4 48
T5.5 | Testing, updating and optimizing online platform
T6.1 | Development of the platform | bar: Year 1 3 to Year 1 12
T6.2 | Content structure organisation of the platform | bar: Year 2 15 to Year 4 48
T6.3 | Publish open source software modification on online repositories | bar: Year 2 15 to Year 4 48
T6.4 | Platform adaptation to the feedback from stakeholders | bar: Year 3 30 to Year 3 33
T6.5 | Develop and employ a tool to search in and compare relevant topics across countries on the platform | bar: Year 3 30 to Year 4 48
T6.6 | Evaluation of efficiency of information retrieval on the platform | bar: Year 3 36 to Year 4 48
T6.7 | Steady-state maintenance of the platform | bar: Year 3 36 to Year 4 48
T7.1 | Structuring community development | bar: Year 1 3 to Year 1 12
T7.2 | Fostering community awareness of the platform | bar: Year 1 6 to Year 3 30
T7.3 | Creating platform endorsement | bar: Year 3 27 to Year 3 33
T7.4 | Extended platform development and community engagement | bar: Year 3 33 to Year 4 48
T7.5 | Fostering long term sustainability | bar: Year 4 42 to Year 4 48
|  | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48