## Worksheet
Milestone number | Milestone title | Related work package | Lead beneficiary | Means of verification | Due date (in month)
MS1 | The first BiCIKL data hackathon held with partners and selected invitees | WP1 | Lifewatch | Meeting attendance list | 4
MS2 | Third Global Biodiversity Informatics Conference (GBIC3) | WP2 | GBIF | Meeting and presentation of draft network graph | 15
MS3 | Network graph database | WP2 | GBIF | Presentation and online dashboard | 15
MS4 | Workshop for training needs identification | WP2 | GETAF | Report on the Workshop outcomes | 20
MS5 | Training Modules on data liberation or publishing tools pilot activity | WP2 | CETAF | Modules uploaded in the BiCIKL Tool Platform | 29
MS6 | Best Practices and recommendations (from T3.3) translated into training material | WP2 | CETAF | Report uploaded in the BiCIKL Tool Platform | 29
MS7 | Communication strategy | WP3 | Pensoft | Report | 6
MS8 | Biodiversity Knowledge Hub prototype | WP3 | Lifewatch | Website | 12
MS9 | Dissemination plan revision | WP3 | CETAF | Report | 24
MS10 | Workshop with RIs | WP3 | CETAF | Meeting | 24
MS11 | Workshop with publishers | WP3 | CETAF | Meeting | 28
MS12 | Biodiversity Knowledge Hub Best Practices communicated to T2.3 | WP3 | Lifewatch | Report | 29
MS13 | Outreach activities report I | WP3 | CETAF | Report | 12
MS14 | Outreach activities report II | WP3 | CETAF | Report | 24
MS15 | Project call process definition phase completed | WP4 | ELIXIR/EMBL-EBI | Report | 3
MS16 | Pilot call projects process opens | WP4 | ELIXIR/EMBL-EBI | Call for pilot project proposals is made public via the BiCIKL web site and other channels | 12
MS17 | Full call projects process opens | WP4 | ELIXIR/EMBL-EBI | Call for full project proposals is made public via the BiCIKL web site and other channels | 24
MS18 | Initial teleconference between infrastructures and follow-on regular TCs will have been established and set up | WP5 | ELIXIR/EMBL-EBI | Meeting minutes | 3
MS19 | External board review received I | WP5 | ELIXIR/EMBL-EBI | Report | 12
MS20 | External board review received II | WP5 | ELIXIR/EMBL-EBI | Report | 24
MS21 | External board review received III | WP5 | ELIXIR/EMBL-EBI | Report | 36
MS22 | Specification of the independent authoring and editing environment | WP6 | Pensoft | Report | 6
MS23 | Initial scoping and assessment of optimal degree of automation for processing workflow | WP6 | Plazi | Report | 9
MS24 | Prototype implementation of proposed advanced automation tools | WP6 | Plazi | Product | 21
MS25 | Beta-implementation and deployment of automated data extraction and preparation service | WP6 | Plazi | Product | 30
MS26 | Scoping and specifications for workbench | WP6 | Plazi | Report | 12
MS27 | App specifications | WP6 | Pensoft | Report | 10
MS28 | Architecture design ready for evaluation by potential end users; design and specification report. | WP7 | Naturalis | Report | 9
MS29 | PID system development roadmap and technical provisioning for test system (beta/pre-production) | WP7 | Naturalis | Roadmap, beta PID system | 14
MS30 | Draft recommendation for specimen links in sequence data | WP7 | FUB-BGBM | Report | 24
MS31 | Full data and API specification for specimen links in sequence data | WP7 | FUB-BGBM | Report | 27
MS32 | The design and prototype of a workflow integrating Wikidata into validation and linking | WP7 | MeiseBG | Report | 25
MS33 | Documentation on how to interface with FAIR Digital Object via Digital Object Interface Protocol (DOIP) | WP7 | Naturalis | Documentation | 27
MS34 | Report on profile of sequenced material source annotations | WP8 | EMBL | Report | 6
MS35 | Submission for publication of “application note” relating to sequenced material source validation tool | WP8 | ELIXIR/EMBL-EBI | Manuscript | 14
MS36 | First improved sequenced material source annotations routed through the ELIXIR Contextual Data Clearinghouse | WP8 | UTARTU | News item | 6
MS37 | Specification for curation workbench | WP10 | GBIF | Report | 12
MS38 | Implementation of workbench released for use by taxonomic users | WP10 | GBIF | Product | 21
MS39 | Specification for encapsulated services | WP10 | Sp2000 | Report | 18
MS40 | Integration of encapsulated service into first partner infrastructure | WP10 | Sp2000 | Product | 27
MS41 | Implementation of mapping visualisation released | WP10 | Sp2000 | Product | 27
MS42 | Gathering of a limited set of biodiversity-related questions | WP11 | Plazi | CSV database | 6
MS43 | Mockups to support the design of the link association services | WP11 | Naturalis | Presentation | 15
MS44 | Mockups to support the design of the workbench | WP11 | Plazi | Presentation | 28
MS45 | Advisory Board Members appointed | WP12 | Pensoft | Letters of intent | 3
MS46 | Kick off meeting | WP12 | Pensoft | Meeting report at M2 | 1
MS47 | Second Annual GA meeting held | WP12 | Pensoft | Meeting report | 18
MS48 | Third Annual GA meeting held | WP12 | Pensoft | Meeting report | 34