## Worksheet
WP No. | 1 | Lead beneficiary | KNOW | Start month | 1 | End month | 36
WP title | Coordination and Management
ObjectivesThis work package aims to oversee & coordinate the financial, & day-to-day activities of TIER2 to ensure the achievement of the project’s overall aims & objectives. Specifically, it will coordinate all activities in the project & ensure that partners work together effectively & facilitate the scientific, research & impact success of the project through careful monitoring of progress, management of resources, open communication, & coordination of activities within the time & budget constraints of the project. Additionally, it ensures the project meets its contractual commitments & predicts, mitigates & overcomes project-related risks. WP1 develops plans to ensure the project activities meet the highest ethical, legal, integrity & quality assurance standards. It provides efficient operational management support including administrative & financial planning, reporting to the EC, & management of project legal aspects including project-related contracts & IPR, & management of day-to-day operational & technical progress. Finally, it sets up an international advisory board.
Description of workTask 1.1 Scientific and administrative coordination (M1-36; KNOW [lead], ARC, VUmc)Scientific & administrative coordination tasks include the following: * Coordinate the Grant Agreement, Consortium Agreement, & signature procedures; * Develop, disseminate & monitor adherence to a Project Management, Research Integrity Plan, a Quality Assurance Plan, Data Management Plan, & a Publications Agreement; * Coordinate ethics deliverables; * Support communication & collaboration between WPs, & the alignment & integration of work between them; * Implement & maintain internal reporting & monitoring procedures (including internal review procedures, gender distribution in the consortium composition, & sex, gender & diversity considerations in the project activities); * Monitor & support the completion on schedule of deliverables & milestones & take corrective action in the case of delays; * Mediate in cases of internal disputes; * Organise the General Assembly, Executive Board & Advisory Board meetings * Handle daily project correspondence & requests from partners & external bodies; * Produce periodic & final reports for the EC. Task 1.2 Financial Coordination (M1-36; KNOW [lead])Financial coordination tasks include: * Calculate & distribute EC payments to project beneficiaries according to the Consortium Agreement; * Liaise with finance departments to monitor contracts; * Maintain financial records; * Coordinate financial statements submission by all project partners; * Provide financial overviews for the periodic & final reports for the EC. Task 1.3. TIER2 Open and reproducible research practices (M1-36; ARC [lead], KNOW, AU)Throughout the project, TIER2 will itself adhere to radical reproducibility & transparency. This task will ensure best practices, including adherence to Horizon Europe requirements on Research Data Management & Open Science, & take an auto-ethnographic approach to study our own project as a case study. It will ensure TIER2 adheres to state-of-the-art practices for reproducibility (e.g., pre-registration, reporting of negative results, sharing of protocols, methods, code, data). It will reflect upon the challenges, costs & benefits resulting from such reproducibility & transparency approaches in the context of international, multidisciplinary project consortia. This will lead to a final self-reflection report & feed into the synthesis of results obtained from the empirical work in WPs 3-5. Task 1.4. Strategic alignment activities (M1-M36; OpenAIRE [lead], KNOW, Charite)A unique selling point for TIER2 is our position at the nexus of various existing networks & initiatives (Reproducibility Networks, EOSC, other infrastructures, funder/publisher networks) whose effective alignment will bring powerful network effects. As two projects are foreseen to be funded via this HORIZON-WIDERA-2022-ERA-01-41 call, we also identify effective collaboration with the other project to be funded as a priority to avoid overlaps & duplications. This task ensures this alignment, coordinated via OpenAIRE & its network of actors in more than 30 countries covering the EC & beyond.
DeliverablesD1.1 Project handbook (including management, research integrity & quality assurance plans) (KNOW, M4)D1.2 Data Management Plan (ARC, M6)D1.3 Data Management Plan (Update) (ARC, M18)D1.4 Autoethnographic reflections on implementing radical reproducibility in the TIER2 project (AU, M36)