## Worksheet
WP No. | 2 | Lead beneficiary | PENSOFT | Start month | 1 | End month | 36
WP title | Communities, Communication and Dissemination
ObjectivesThis work package builds the TIER2 network to coordinate community engagement, co-creation activities, fluid outreach/dissemination & hence build capacity for skills & knowledge amongst all actors. This includes building communities & networks to foster & strengthen communication with all key stakeholders in reproducibility & increase awareness/skills for reproducibility tools & practices across disciplines. The WP will: Create a stakeholder map & engagement plan; Co-ordinate the co-creation communities for WPs 3, 4 & 5; Create the Reproducibility Hub to showcase state-of-the-art knowledge, tools & practices for reproducibility; Ensure effective communication (within the project) & dissemination of outcomes (beyond the project).
Description of workTask 2.1. Stakeholder mapping (M1-M3; KNOW [lead], OpenAIRE, Charite)As a first task in TIER, we conduct in-depth stakeholder analysis to identify the key players & stakeholders for engagement in co-creation, communication, dissemination & exploitation (cf. provisional analysis section 2.2.2). Using the 5Rs framework, we will analyse each stakeholder’s potential impact & influence within the project (incl. “push-pull” factors) to identify key stakeholders, structures of decision-making, where relationships can/should be strengthened, & resources required. This process will explore/identify key channels/methods/platforms for engagement with each group. The Stakeholder Map will be a key resource underpinning all co-creation & communication/dissemination activities, help structure Task 3.2 (evidence mapping), & underpin classification of resources on the Reproducibility Hub (Task 2.3). Task 2.2. Community development and coordination of co-creation activities (M1-M36; Charite [lead], KNOW, VUmc, PENSOFT, OpenAIRE, UOXF)Co-creation is an essential element of TIER2, with co-design & piloting activities with communities of researchers (soc, life, comp sci), publishers & funders, forming the backbone of the project. To ensure successful community-management & effective coordination of activities across WPs3-5, we hence dedicate a specific task. Building heavily on our existing links to the Reproducibility Networks, EOSC (incl. EOSC-Life & SSHOC) & publisher/funder fora, we use platforms/ strategies outlined in D2.1 “Stakeholder Communication & Engagement Plan” to offer co-creation communities a unique value proposition underpinned by support activities to facilitate engaged participation (as outlined in sec 1.2.2.2). Within each case study domain, we will identify groups of reproducibility “champions” to spread awareness of initiatives & tools. We will hold virtual brainstorming events or “BarCamps” to co-create whitepapers on topics such as needs-gap analyses, barriers & enabler assessments, & virtual “co-working” events or “hackathons” to promote & improve reproducibility tools developed & piloted in WPs4/5. To build the network of Reproducibility Networks, we will hold an open call (deadline M9, eligible only to Widening Participation countries), where consortia of 3 or more institutions within a county will be able to apply for one of 3 awards of 5k EUR to fund a first meeting to establish an RN in their country. Task 2.3. Development of the Reproducibility Hub (M10-M36; VUmc [lead], KNOW, GESIS, OpenAIRE)This task will develop the Reproducibility Hub as a sub-site of The Embassy of Good Science (hosted by task leader VUmc). The Reproducibility Hub will iteratively combine content from across the project as a knowledge-base of reproducibility tools & best practices for TIER2 stakeholders (researchers, funders, publishers & beyond). The Hub, a wiki-based web-based platform, will use interactive modes of presentation, combining curated checklists, community engagement functionalities, five introductory training modules & in-depth articles on key topics & training materials. FAIRsharing & OpenAIRE data will power interactive graphs that visualise the landscape of reporting standards & best practices (for data, metadata & software), & their relations, as well as their use (by the EOSC clusters) & their adoption by data policies (by funders & publishers). The Hub’s relevance beyond the project’s lifetime will be ensured by its curation within The Embassy, whose governing foundation is already committed to its long-term sustainability. To this end, activities will include workshops hosted at domain-specific conferences to boost dissemination to stakeholders & to provide training on how to contribute to the Hub's content. We will leverage network effects offered by communities from OpenAIRE, FAIRsharing (including the newly launched EOSC-Future/RDA FAIRsharing Community Curation Programme) & the Reproducibility Networks to initiate community-led processes to update content beyond the project’s runtime. In developing the Reproducibility Hub & engaging the wider community to ensure its success, we will strive to leverage synergies with any other EC projects, especially the second project funded under this call. Task 2.4. Project dissemination and communication (M1-M36; PENSOFT [lead], KNOW, ARC, VUmc, AU, OpenAIRE, Charite)This task will manage all TIER2 dissemination & communication activities. Building on the provisional dissemination & communication plan described in Section 2.2, this task will ensure the project is optimally promoted to targeted audiences & to the most important stakeholders across Europe. The revised dissemination plan will outline a strategic communication campaign including a social media strategy, which will be updated periodically (D2.1) to ensure targeted communication strategies for the different project phases. Specific activities include the development of a dissemination toolkit, including a professional corporate identity, communication & dissemination materials as well as templates to be used for presentations, reports, meetings & internal documents, within the first six months of the project. This includes a public project website, which will showcase the project’s activities & results both to the scientific/policy community as well as to the public at large. It will coordinate regular dissemination of project progress & results via press releases, news entries & blogs. Further dissemination materials will be created for the purpose of communicating project activities & results (e.g., posters, stickers & other materials for events). As part of the communication plan, publication guidelines will be developed that regulate authorship & specify measures to ensure transparency of methods & reproducibility of project results. This task will also provide organisational support for TIER2’s final project cross-stakeholder conference. The conference will provide a forum to showcase TIER2 results, share reflections on the team’s practices in terms of reproducible research, & present the recommendations from Task 3.3.
Deliverables:D2.1 Stakeholder Communication & Engagement Plan (PENSOFT, M6)D2.2 Stakeholder Communication & Engagement Plan (First Update) (PENSOFT, M24)D2.3 Reproducibility Hub (Resource/website) (VUmc, M36)D2.4 Stakeholder Communication & Engagement Plan (Second Update) (PENSOFT, M36)D2.5 Policy Briefing 1 (KNOW, M12)D2.6 Policy Briefing 2 (KNOW, M36)Milestones:MS2.1 Reproducibility Hub (Beta version) (M15)MS2.2 Final self-reflection report on co-creation processes (M34)MS2.3 Final conference (M36)MS2.4 Website and Logo (M2)