## BiCIKL Project Plan
tType | tID | tDependency | tDependents | tStartConstrain | tEndConstrain | TIL | SS | TaskType | WBS | Task | TaskLead | TaskLeadCost | BSD | BED | BD | ESD | EED | ED | PercentageCompleted | ASD | AED | AD | BCS | ECS | ACS | Notes | TColor | TPColor | BLColor | LC |  | TimelineStart | [34 empty] | TimelineEnd
System | System |  | System | System | System | System | 1 | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System
[32 empty] | 44197 | 44228 | 44256 | 44287 | 44317 | 44348 | 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047 | 45078 | 45108 | 45139 | 45170 | 45200 | 45231 | 45261
[10 empty] | Time table of project implementation | [21 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
[10 empty] | (tasks, milestones and deliverables) | [21 empty] | Month | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
tType | tID | tDependency | tDependents | tStartConstrain | tEndConstrain |  |  | Cat. | № | Item | Lead | Resource Cost | Baseline Start | Baseline End | Baseline Duration | Start | Finish | Duration | Percent Complete | Actual Start | Actual End Date | Actual Duration | Baseline Cost | Cost | Actual Cost | Notes | Bar Color | % Color | Baseline Color |  | PM | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56
[8 empty] | Pillar 1 |  | NETWORKING ACTIVITIES [NA]
T | 1 |  |  |  |  | 0 |  | WP | 1 | NA-01 Coordination and interoperability of infrastructures through harmonisation of community policies, standards and guidelines | MBG |  | 2021-05-30 | 2022-06-30 | 284 | 2021-05-30 | 2022-06-30 | 284 | 0%
T | 2 |  |  |  |  | 1 |  | T | 1.1 | A technical user requirements analysis | LIFEWATCH |  | 2022-01-03 | 2022-01-03 | 1 | 2022-01-03 | 2022-01-03 | 1 | 0% | [11 empty] | 8 | bar: Year 1 Feb to Year 1 Dec
M | 39 |  |  |  |  | 2 |  | D | 1.1 | User requirements analysis report | LIFEWATCH |  | 2022-01-03 | 2022-01-03 | 1 | 2021-01-03 | 2022-01-03 | 1 | 0% | [12 empty] | Year 1 Apr: MS1; Year 1 Dec: D1.1
T | 4 |  |  |  |  | 1 |  | T | 1.2 | Testing and streamlining interoperability | MBG |  | 2021-05-30 | 2021-05-31 | 1 | 2021-05-30 | 2021-05-31 | 1 | 0% | [11 empty] | 8 | bar: Year 1 Month to Year 1 Oct
M | 40 |  |  |  |  | 2 |  | D | 1.2 | Recommendations for interoperability among infrastructures | MBG |  | 2021-05-30 | 2021-05-31 | 1 | 2021-05-30 | 2021-05-31 | 1 | 0% | [12 empty] | Year 1 Oct: D1.2
T | 3 |  |  |  |  | 1 |  | T | 1.3 | Findability, reuse and accessibility alignment | Naturalis |  | 2022-06-30 | 2022-06-30 | 1 | 2022-06-30 | 2022-06-30 | 1 | 0% | [11 empty] | 8 | bar: Year 1 Jun to Year 2 Jun
M | 41 |  |  |  |  | 2 |  | D | 1.3 | Best practice manual for findability, re-use and accessibility of infrastructures | Naturalis |  | 2022-06-30 | 2022-06-30 | 1 | 2022-06-30 | 2022-06-30 | 1 | 0% | [12 empty] | Year 2 Jun: D1.3
T | 5 |  |  |  |  | 0 |  | WP | 2 | Defining & co-designing the Biodiversity Knowledge Hub (BKH) and operational training | GBIF |  |  |  |  | 2020-01-30 | 2020-01-31 | 2 | 0%
T | 6 |  |  |  |  | 1 |  | T | 2.1 | Identify and establish the necessary operational framework | GBIF |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | bar: Year 1 Month to Year 2 Mar
M | 42 |  |  |  |  | 2 |  | D | 2.1 | Relational network graph for the Biodiversity Knowledge Hub (BKH) | GBIF |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [12 empty] | Year 2 Mar: D2.1
MS2
T | 7 |  |  |  |  | 1 |  | T | 2.2 | Identify the components of the Biodiversity Knowledge Hub | GBIF |  |  |  |  | 2020-01-30 | 2020-01-30 | 1 | 0% | bar: Year 1 Feb to Year 2 Mar
[8 empty] | D | 2.2 | Stakeholder input into the network graph provided by Third Global Biodiversity Informatics Conference (GBIC3) [M15] | GBIF | [20 empty] | Year 2 Mar: D2.2
MS3
T | 8 |  |  |  |  | 1 |  | T | 2.3 | Translate the operational framework and functional network graph into an educational cloud | CETAF |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | bar: Year 2 Mar to Year 3 Jun
M | 43 |  |  |  |  | 2 |  | D | 2.3 | BiCKL training programme [MOOC] [M30] | CETAF |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [12 empty] | Year 2 Aug: MS4; Year 3 May: MS5; Year 3 Jun: D2.3
MS6
T | 9 |  |  |  |  | 0 |  | WP | 3 | NA-03 Implementation, stakeholder engagement and outreach for the Biodiversity Knowledge Hub | CETAF |  | 2021-06-30 | 2023-12-29 | 653 | 2021-06-30 | 2023-12-29 | 653 | 0%
T | 10 |  |  |  |  | 1 |  | T | 3.1 | Community branding, website and communication platform | Pensoft |  | 2021-06-30 | 2021-06-30 | 1 | 2021-06-30 | 2021-06-30 | 1 | 0% | bar: Year 1 Month to Year 1 Jun
M | 44 |  |  |  |  | 2 |  | D | 2020-01-03 | Project logo, marketing pack and website design and development [M3] | Pensoft |  | 2021-06-30 | 2021-06-30 | 1 | 2021-06-30 | 2021-06-30 | 1 | 0% | [12 empty] | Year 1 Mar: D3.1; Year 1 Jun: MS7
T | 11 |  |  |  |  | 1 |  | T | 3.2 | Engagement and dissemination | CETAF |  | 2021-06-30 | 2023-12-29 | 653 | 2021-06-30 | 2023-12-29 | 653 | 0%
M | 45 |  |  |  |  | 2 |  | D | 3.2 | Plan for Dissemination and Exploitation of Project results | CETAF |  | 2021-06-30 | 2021-06-30 | 1 | 2021-06-30 | 2021-06-30 | 1 | 0% | [12 empty] | Year 1 Jun: D3.2; Year 1 Dec: MS8; Year 2 Dec: MS9; Year 3 Apr: MS11
M | 46 |  |  |  |  | 2 |  | D | 3.3 | Outreach initiatives report [M36] | CETAF |  | 2023-12-29 | 2023-12-29 | 1 | 2023-12-29 | 2023-12-29 | 1 | 0% | [12 empty] | Year 2 Dec: MS10; Year 3 Dec: D3.3
MS14
T | 12 |  |  |  |  | 1 |  | T | 3.3 | Implementation of the BKH and outreach | LIFEWATCH |  | 2022-01-03 | 2022-01-03 | 1 | 2022-01-03 | 2022-01-03 | 1 | 0%
M | 47 |  |  |  |  | 2 |  | D | 3.4 | The Biodiversity Knowledge Hub (BKH) [M24] | LIFEWATCH |  | 2022-01-03 | 2022-01-03 | 1 | 2022-01-03 | 2022-01-03 | 1 | 0% | [12 empty] | Year 1 Dec: MS13; Year 2 Dec: D3.4; Year 3 May: MS12
[8 empty] | Pillar 2 |  | ACCESS: Transnational and Virtual Access
T | 13 |  |  |  |  | 0 |  | WP | 4 | TA Transnational access to biodiversity infrastructure and services | ELIXIR Hub |  |  |  |  | 2020-01-30 | 2020-01-30 | 1 | 0%
[8 empty] | T | 2020-01-04 | Define the process for how the project calls for the users of the BiCIKL community will be run | ELIXIR Hub | bar: Year 1 Month to Year 1 Mar
[8 empty] | D | 4.1 | Project call definition and execution plan, published via BiCIKL web-site | ELIXIR Hub | [20 empty] | Year 1 Mar: D4.1
[8 empty] | T | 2020-02-04 | Run the pilot phase project call | ELIXIR Hub | [20 empty] | Year 1 Mar: MS15
[8 empty] | D | 4.2 | Report on pilot call process | ELIXIR Hub | [20 empty] | Year 1 Dec: MS16; Year 2 Dec: D4.2
[8 empty] | T | 2020-03-04 | Run the full project call process | ELIXIR Hub | bar: Year 3 Jan to Year 3 Dec
[8 empty] | D | 4.3 | Report on full call process | ELIXIR Hub | [20 empty] | Year 2 Dec: MS17; Year 3 Dec: D4.3
[8 empty] | T | 2020-04-04 | Management and distribution of BiCIKL funds to infrastructures to support trans-national access via project calls | ELIXIR Hub
[8 empty] | T | 2020-05-04 | Formulate and report a long term plan for how the service offered by the BiCIKL community could be offered in the future | ELIXIR Hub | bar: Year 3 Apr to Year 3 Dec
[8 empty] | D | 4.4 | Report on a long term sustainability plan for the BiCIKL community services | ELIXIR Hub | [20 empty] | Year 3 Dec: D4.4
T | 14 |  |  |  |  | 0 |  | WP | 5 | Virtual access to biodiversity infrastructure and services | ELIXIR Hub |  |  |  |  | 2020-01-30 | 2020-01-30 | 1 | 0%
[8 empty] | T | 2020-01-05 | Coordination of virtual access across the named infrastructures | ELIXIR Hub
[8 empty] | D | 5.1 | World class virtual access to the infrastructures in support of Biodiversity and related subject matter research is provided | ELIXIR Hub | [20 empty] | Year 1 Mar: MS18; Year 3 Dec: D5.1
[8 empty] | T | 5.1.1 | Annual review of the BiCIKL infrastructures | ELIXIR Hub | bar: Year 1 Sep to Year 3 Dec
[8 empty] | T | 5.1.2 | Summaries of each infrastructure, their tools and services | ELIXIR Hub | bar: Year 1 Sep to Year 1 Dec; Year 2 Sep to Year 2 Dec; Year 3 Sep to Year 3 Dec
[8 empty] | D | 5.2 | Periodic assessments of VA by external board and a final assessment report | ELIXIR Hub | [20 empty] | Year 1 Dec: MS19; Year 2 Dec: MS20; Year 3 Dec: D5.2
MS21
[8 empty] | Pillar 3 |  | JOINT RESEARCH ACTIVITIES | MBG
T | 15 |  |  |  |  | 0 |  | WP | 6 | JRA-01 Liberation of data from literature, next-generation semantic publishing and delivery of FAIR data | Plazi |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0%
T | 16 |  |  |  |  | 1 |  | T | 6.1 | Develop novel publishing tools and workflows for structured, standards-aligned content | Pensoft |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [11 empty] | 12 | bar: Year 1 Mar to Year 2 Dec
[8 empty] | D | 6.1 | Enhanced, standalone and freely accessible installation of the ARPHA Writing Tool (AWT) | Pensoft | [20 empty] | Year 1 Jun: MS22; Year 2 Dec: D6.1
M | 50 |  |  |  |  | 2 |  | T | 2020-02-06 | Liberation, enhancement, management and distribution of data from literature | Plazi |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0%
[8 empty] | D | 6.2 | Automated workflow for discovery, semantic enhancement, mapping, extraction, FAIRfying, and dissemination of data liberated from literature | Plazi | [20 empty] | Year 1 Sep: MS23; Year 2 Sep: MS24; Year 3 Jun: MS25; Year 3 Dec: D6.2
T | 18 |  |  |  |  | 1 |  | T | 2020-03-06 | Federated FAIR data system through aligned identifiers | Plazi |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [11 empty] | 3 | bar: Year 1 Sep to Year 2 Jun
[8 empty] | D | 6.3 | A workflow for bi-directional linking of data from literature to external resources [M18]. | Plazi | [20 empty] | Year 1 Dec: MS26; Year 2 Jun: D6.3
T | 19 |  |  |  |  | 1 |  | T | 6.4 | Integrating published narrative and Linked Open Data | Pensoft |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [11 empty] | 3 | bar: Year 1 Sep to Year 2 Aug
[8 empty] | D | 6.4 | Applications for interoperable access to OpenBiodiv through semantically enhanced queries [M20] | Pensoft | [20 empty] | Year 1 Oct: MS27; Year 2 Aug: D6.4
T | 20 |  |  |  |  | 0 |  | WP | 7 | JRA-02 Providing core access services and FAIR data on specimens and samples | Naturalis |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0%
T | 21 |  |  |  |  | 1 |  | T | 7.1 | Rolling out a pan-European PID system for Digital Specimens | Naturalis |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [11 empty] | 11.5 | bar: Year 1 Mar to Year 2 Jun
M | 53 |  |  |  |  | 2 |  | D | 7.1 | Architecture Design for a pan-European PID system for Digital Specimens | Naturalis |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [12 empty] | Year 1 Sep: MS28; Year 2 Feb: MS29; Year 2 Jun: D7.1
T | 22 |  |  |  |  | 1 |  | T | 7.2 | Establishing functional links between specimens and other data classes | BGBM-FUB |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [11 empty] | 13 | bar: Year 1 Dec to Year 3 Jun
M | 54 |  |  |  |  | 2 |  | D | 7.2 | Data standards and workflows for linking sequence data with specimens implemented and published. | BGBM-FUB |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [12 empty] | Year 2 Dec: MS30; Year 3 Mar: MS31; Year 3 Jun: D7.2
T | 23 |  |  |  |  | 1 |  | T | 7.3 | Using wikidata to link and validate entities discovered in specimens and literature | MBG |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [11 empty] | 10 | bar: Year 2 Aug to Year 3 Jun
M | 55 |  |  |  |  | 2 |  | D | 7.3 | A repeatable informatics workflow that links people and places to stable identifiers of those entities, including a validation and preservation step | MBG |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0% | [12 empty] | Year 3 Jan: MS32; Year 3 Jun: D7.3
[8 empty] | T | 7.4 | Providing specimens information as FAIR Digital Objects | Naturalis | [19 empty] | 3 | bar: Year 2 Apr to Year 3 Dec
[8 empty] | D | 7.4 | Digital Object Interface Protocol enabled (DOIP) Digital Object repository installation to store and provide digital specimen information. | Naturalis | [20 empty] | Year 3 Mar: MS33; Year 3 Dec: D7.4
T | 24 |  |  |  |  | 0 |  | WP | 8 | JRA-03 A data foundation for connected molecular, natural history collections and taxonomic data | EMBL-EBI |  | 2021-12-31 | 2022-06-30 | 130 | 2021-08-31 | 2023-12-29 | 609 | 0%
T | 25 |  |  |  |  | 1 |  | T | 8.1 | Profiling of existing source annotations, at-scale curation and data services | EMBL-EBI |  |  |  |  | 2021-08-31 | 2021-08-31 | 1 | 0% | [11 empty] | 12 | bar: Year 1 Month to Year 2 Aug
M | 56 |  |  |  |  | 2 |  | D | 8.1 | Availability via API of single, harmonised sequenced material source annotations in ENA [M20] | EMBL-EBI |  |  |  |  | 2021-08-31 | 2021-08-31 | 1 | 0% | [12 empty] | Year 1 Jun: MS34; Year 2 Aug: D8.1
T | 26 |  |  |  |  | 1 |  | T | 8.2 | Data submissions tools and user workflows to capture improved sequenced material source annotations at point of deposition | EMBL-EBI |  | 2021-12-31 | 2021-12-31 | 1 | 2021-12-31 | 2021-12-31 | 1 | 0% | [11 empty] | 10 | bar: Year 1 Jul to Year 2 Jun
M | 57 |  |  |  |  | 2 |  | D | 8.2 | Validation tool open-source software release [M18] | EMBL-EBI |  | 2021-12-31 | 2021-12-31 | 1 | 2021-12-31 | 2021-12-31 | 1 | 0% | [12 empty] | Year 2 Feb: MS35; Year 2 Jun: D8.2
T | 27 |  |  |  |  | 1 |  | T | 8.3 | Operation of the ELIXIR Contextual Data Clearinghouse for the reporting of source material annotation gaps and inaccuracies | UTARTU |  | 2022-06-30 | 2022-06-30 | 1 | 2022-06-30 | 2022-06-30 | 1 | 0% | [11 empty] | 6 | bar: Year 1 Feb to Year 1 Sep
M | 58 |  |  |  |  | 2 |  | D | 8.3 | Web interface for ELIXIR Contextual Data Clearinghouse [M9] | UTARTU |  | 2022-06-30 | 2022-06-30 | 1 | 2022-06-30 | 2022-06-30 | 1 | 0% | [12 empty] | Year 1 Jun: MS36; Year 1 Sep: D8.3
T | 28 |  |  |  |  | 1 |  | T | 8.4 | Creation of a data repository, with submission and access tools, for molecular ecology data | EMBL-EBI |  |  |  |  | 2022-12-31 | 2023-01-02 | 1 | 0% | [11 empty] | 16 | bar: Year 1 Jun to Year 2 Dec
M | 59 |  |  |  |  | 2 |  | D | 8.4 | First submission and access tools available for BIOM data [M24] | EMBL-EBI |  |  |  |  | 2022-12-31 | 2023-01-02 | 1 | 0% | [12 empty] | Year 2 Dec: D8.4
[8 empty] | WP | 9 | Ethics requirements | Pensoft
[8 empty] | T | 9.1 | Ethics management | Pensoft
[8 empty] | D | 9.1 | POPD - Requirement No. 1 | Pensoft | [20 empty] | Year 1 Feb: D9.1
[8 empty] | WP | 10 | JRA-04 Delivering a trusted and evolving taxonomic framework for data integration | Sp2000
[8 empty] | T | 10.1 | Automated ingestion of published taxonomic information | GBIF | [19 empty] | 5 | bar: Year 1 Feb to Year 3 Jun
[8 empty] | D | 10.1 | New and updated taxonomic data products automatically visible in taxonomic framework. | GBIF | [20 empty] | Year 1 Dec: MS37; Year 3 Jun: D.10.1
[8 empty] | T | 10.2 | Data mapping for taxonomic information | GBIF | [19 empty] | 6 | bar: Year 1 May to Year 2 Dec
[8 empty] | D | 10.2 | Workflow for bi-directional linking of taxonomic references to literature [M24] | GBIF | [20 empty] | Year 2 Sep: MS38; Year 2 Dec: D.10.2
[8 empty] | T | 10.3 | Curation and validation of taxonomic information | Sp2000 | [19 empty] | 6 | bar: Year 1 Feb to Year 2 Jun
[8 empty] | D | 10.3 | Validation and curation workbench for taxonomic data | Sp2000 | [20 empty] | Year 2 Jun: D.10.3
[8 empty] | T | 10.4 | Delivery and presentation of taxonomic information | Sp2000 | [19 empty] | 12 | bar: Year 1 May to Year 3 Mar
[8 empty] | D | 10.4 | Web visualisation of mappings between CoL and other checklists [M12] | Sp2000 | [20 empty] | Year 1 Dec: D.10.4; Year 2 Jun: MS39; Year 3 Mar: MS40
[8 empty] | D | 10.5 | CoL services for direct encapsulated use within search and discovery services of BiCIKL partner infrastructures [M27] | Sp2000 | [20 empty] | Year 3 Mar: D.10.5
[11 empty] | Sp2000 | [20 empty] | Year 3 Mar: MS41
[8 empty] | WP | 11 | JRA-05 FAIR Data Place: linking, finding and access | SIB
[8 empty] | T | 11.1 | Benchmarking collection | Plazi | [19 empty] | 2 | bar: Year 1 May to Year 1 Dec
[8 empty] | D | 11.1 | Evaluation benchmark: a database of questions associated with a set of relevant articles (e.g. PMIDs) to measure the progress of the WP towards an effective search service | Plazi | [20 empty] | Year 1 Jun: MS42; Year 1 Dec: D11.1
[8 empty] | T | 11.2 | Distributed search, link prediction and validation | Naturalis | [19 empty] | 16 | bar: Year 1 Mar to Year 2 Jun
[8 empty] | D | 11.2 | Search and link association services: A RESTful API, which will input a link/accession number and return a ranked list of neighbors links with a confidence score [M18] | Naturalis | [20 empty] | Year 2 Mar: MS43; Year 2 Jun: D11.2
[8 empty] | T | 11.3 | Passage retrieval | SIB | [19 empty] | 8 | bar: Year 1 Nov to Year 2 Jun
[8 empty] | D | 11.3 | Passage retrieval services: A RESTful API, which will input a set of keywords and return a set of articles/passages ranked by relevance[M18] | SIB | [20 empty] | Year 2 Jun: D11.3
[8 empty] | T | 11.4 | Factoid question-answering | SIB | [19 empty] | 7 | bar: Year 2 Jun to Year 2 Dec
[8 empty] | D | 11.4 | Factoid question-answering: A RESTful API, which will input a factoid question in natural language and extract a short answer out of the articles/passages returned by D10.3 [M24] | SIB | [20 empty] | Year 2 Dec: D11.4
[8 empty] | T | 11.5 | Search and Question-Answering Portal | Plazi | [19 empty] | 9 | bar: Year 3 Jan to Year 3 Aug
[8 empty] | D | 11.5 | Workbench implementation: a set of responsive Graphic User Interfaces developed in HTML 5.x/JavaScript to operate the aforementioned services. [M32] | Plazi | [20 empty] | Year 3 Apr: MS44; Year 3 Aug: D11.5
T | 30 |  |  |  |  | 0 |  | WP | 12 | Project Management | Pensoft |  | 2021-02-26 | 2022-03-31 | 285 | 2020-01-31 | 2022-03-31 | 565 | 0%
T | 31 |  |  |  |  | 1 |  | T | 12.1 | Detailed project planning and Standard Operational Procedures (SOP) (detailed description of governance structure & mechanisms) | Pensoft |  | 2021-02-26 | 2022-03-31 | 285 | 2021-01-29 | 2022-03-31 | 305 | 0% | bar: Year 1 Month to Year 1 Jun
M | 63 |  |  |  |  | 2 |  | D | 12.1 | Project Work Plan and Standard Operational Procedures | Pensoft |  | 2022-03-31 | 2022-03-31 | 1 | 2022-03-31 | 2022-03-31 | 1 | 0% | [6 empty] | Repeats in month 24 and 33 | [5 empty] | Year 1 Month: D12.1; Year 1 Mar: MS45
M | 36 |  |  |  |  | 3 |  | D | 12.2 | Inception Report (detailed plans of the implementation developed during the Kick-off meeting) | Pensoft |  | 2021-03-31 | 2021-03-31 | 1 | 2021-03-31 | 2021-03-31 | 1 | 0% | [12 empty] | Year 1 Month: D12.2
[8 empty] | D | 12.9 | Data Management Plan | Pensoft | [20 empty] | Year 1 Jun: D12.9
T | 37 |  |  |  |  | 2 |  | T | 12.2 | Organisation of annual General Assembly and monthly Executive Board meetings | Pensoft |  | 2021-02-26 | 2021-02-26 | 1 | 2021-01-29 | 2021-02-03 | 4 | 0%
M | 34 |  |  |  |  | 3 |  | D | 12.3 | General Assembly/Kick off meeting report [GA] [M2] | Pensoft |  |  |  |  | 2021-01-29 | 2021-01-29 | 1 | 0% | [12 empty] | Year 1 Month: MS46; Year 1 Feb: D12.3; Year 2 Jun: MS47
[8 empty] | D | 12.4 | Second General Assembly report | Pensoft | [20 empty] | Year 2 Jun: D12.4; Year 3 Oct: MS48
[8 empty] | D | 12.5 | Third General Assembly report | Pensoft | [20 empty] | Year 3 Oct: D12.5
T | 61 |  |  |  |  | 1 |  | T | 12.3 | Internal communication, document management and archiving | Pensoft |  | 2021-06-30 | 2021-06-30 | 1 | 2021-06-30 | 2021-06-30 | 1 | 0%
[8 empty] | D | 12.6 | Internal communication platform | Pensoft | [20 empty] | Year 1 Apr: D12.6
T | 62 |  |  |  |  | 1 |  | T | 12.4 | Administration and financial management and reporting | Pensoft |  |  |  |  | 2020-01-31 | 2020-01-31 | 1 | 0%
[8 empty] | T | 12.5 | Risk management and quality control | Pensoft
[8 empty] | D | 12.7 | Risk management review I: risk register maintained and updates communicated to Executive Board and beneficiaries | Pensoft | [20 empty] | Year 2 Jun: D12.7
[8 empty] | D | 12.8 | Risk management review II: risk register maintained and updates communicated to Executive Board and beneficiaries | Pensoft | [20 empty] | Year 3 Dec: D12.8
Legend:
- task duration
[36 empty] | Dx.x | - deliverable [numbered]
[36 empty] | Mxx | - milestone [numbered]

## Progress (hidden)
| BiCIKL | Project writing progress
| Date | 2020-11-02
Progress along four major steps
| WBS | Work package and Task | Lead | Task description | Lead/participant | Timing | Effort (pers/mo)
WP | 1 | NA-01 Coordination and interoperability of infrastructures through harmonisation of community policies, standards and guidelines | MBG | 90% | 90% | 0% | 0%
T | 1.1 | A technical user requirements analysis | LIFEWATCH | 90% | 90% | 0% | 0%
D | 1.1 | User requirements analysis report | LIFEWATCH | 100% | 90% | 0% | 0%
T | 1.2 | Testing and streamlining interoperability | MBG | 90% | 90% | 0% | 0%
D | 1.2 | D | MBG | 100% | 100% | 0% | 0%
T | 1.3 | T | Naturalis | 90% | 90% | 0% | 0%
D | 1.3 | 0 | Naturalis | 100% | 100% | 0% | 0%
WP | 2 | T | GBIF | 75% | 33% | 0% | 0%
T | 2.1 | Identify and establish the necessary operational framework | GBIF | 90% | 75% | 0% | 0%
#REF! | 2.1 | Relational network graph for the Biodiversity Knowledge Hub (BKH) | GBIF | 90% | 75% | 0% | 0%
#REF! | 2.2 | Identify the components of the Biodiversity Knowledge Hub | GBIF | 75% | 25% | 0% | 0%
#REF! | 0 | 0 | 0 | 50% | 25% | 0% | 0%
#REF! | 2.3 | Translate the operational framework and functional network graph into an educational cloud | CETAF | 50% | 25% | 0% | 0%
D | 2.3 | BiCKL training programme [MOOC] [M30] | CETAF | 90% | 90% | 0% | 0%
0 | 0 | 0 | 0 | 90% | 90% | 0% | 0%
WP | 1900-01-02 | NA-03 Implementation, stakeholder engagement and outreach for the Biodiversity Knowledge Hub | CETAF | 100% | 100% | 0% | 0%
T | 3.1 | Community branding, website and communication platform | Pensoft | 90% | 90% | 0% | 0%
D | 2020-01-03 | Project logo, marketing pack and website design and development [M3] | Pensoft | 100% | 100% | 0% | 0%
T | 3.2 | Engagement and dissemination | CETAF | 100% | 100% | 0% | 0%
D | 3.2 | Plan for Dissemination and Exploitation of Project results | CETAF | 90% | 90% | 0% | 0%
D | 1900-01-02 07:12 | Outreach initiatives report [M36] | CETAF | 100% | 100% | 0% | 0%
#REF! | #REF! | #REF! | #REF! | 100% | 100% | 0% | 0%
Pillar 2 | 0 | ACCESS: Transnational and Virtual Access | 0 | 90% | 100% | 0% | 0%
WP | 1900-01-03 | TA Transnational access to biodiversity infrastructure and services | ELIXIR Hub | 90% | 100% | 0% | 0%
D | 4.1 | Project call definition and execution plan, published via BiCIKL web-site | ELIXIR Hub | 90% | 100% | 0% | 0%
D | 4.2 | Report on pilot call process | ELIXIR Hub | 90% | 100% | 0% | 0%
D | 4.3 | Report on full call process | ELIXIR Hub | 90% | 100% | 0% | 0%
T | 2020-04-04 | Management and distribution of BiCIKL funds to infrastructures to support trans-national access via project calls | ELIXIR Hub | 90% | 100% | 0% | 0%
T | 2020-01-04 | Define the process for how the project calls for the users of the BiCIKL community will be run | ELIXIR Hub | 90% | 100% | 0% | 0%
T | 2020-02-04 | Run the pilot phase project call | ELIXIR Hub | 90% | 100% | 0% | 0%
T | 2020-03-04 | Run the full project call process | ELIXIR Hub | 90% | 100% | 0% | 0%
T | 2020-05-04 | Formulate and report a long term plan for how the service offered by the BiCIKL community could be offered in the future | ELIXIR Hub | 90% | 100% | 0% | 0%
D | 4.4 | Report on a long term sustainability plan for the BiCIKL community services | ELIXIR Hub | 25% | 0% | 0% | 0%
WP | 1900-01-04 | Virtual access to biodiversity infrastructure and services | ELIXIR Hub | 25% | 25% | 0% | 0%
D | 5.1 | World class virtual access to the infrastructures in support of Biodiversity and related subject matter research is provided | ELIXIR Hub | 25% | 25% | 0% | 0%
T | 5.1.1 | Annual review of the BiCIKL infrastructures |  | 25% | 25% | 0% | 0%
Pillar 3 | 0 | JOINT RESEARCH ACTIVITIES | MBG | 90% | 75% | 50% | 0%
WP | 6 | JRA-01 Liberation of data from literature, next-generation semantic publishing and delivery of FAIR data | Plazi | 90% | 75% | 50% | 0%
#REF! | #REF! | Next-generation, standard-aligned authoring and editorial tool | #REF! | 90% | 75% | 50% | 0%
T | 6.1 | Develop novel publishing tools and workflows for structured, standards-aligned content | Pensoft | 90% | 75% | 50% | 0%
#REF! | #REF! | Improved tools for conversion of PDF-based journals to XML publishing | #REF! | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
D | 6.1 | Liberation, enhancement, management and distribution of data from literature | Pensoft | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
T | 2020-02-06 | Liberation, enhancement, management and distribution of data from literature | Plazi | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
D | 6.2 | Automated workflow for discovery, semantic enhancement, mapping, extraction, FAIRfying, and dissemination of data liberated from literature | Plazi | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
D | 6.3 | #REF! | Plazi | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 90% | 75% | 50% | 0%
#REF! | #REF! | A workflow for bi-directional linking of data from literature to external resources [M18]. | #REF! | 90% | 75% | 50% | 0%
#REF! | #REF! | #REF! |  | 90% | 75% | 50% | 0%
T | 6.4 | Integrating published narrative and Linked Open Data |  | 90% | 75% | 50% | 0%
D | 6.4 | Applications for interoperable access to OpenBiodiv through semantically enhanced queries [M20] | Pensoft | 75% | 0% | 50% | 0%
WP | 7 | JRA-02 Providing core access services and FAIR data on specimens and samples | Naturalis | 75% | 0% | 0% | 0%
T | 7.1 | Rolling out a pan-European PID system for Digital Specimens | Naturalis | 0% | 0%
D | 7.1 | Architecture Design for a pan-European PID system for Digital Specimens | Naturalis | 75% | 0% | 0% | 0%
T | 7.2 | Establishing functional links between specimens and other data classes | BGBM-FUB | 0% | 0%
D | 7.2 | Data standards and workflows for linking sequence data with specimens implemented and published. | BGBM-FUB | 75% | 0% | 0% | 0%
T | 7.3 | Using wikidata to link and validate entities discovered in specimens and literature | MBG | 0% | 0%
T | 7.4 | A repeatable informatics workflow that links people and places to stable identifiers of those entities, including a validation and preservation step |  | 75% | 0%
D | 7.4 | Digital Object Interface Protocol enabled (DOIP) Digital Object repository installation to store and provide digital specimen information. | Naturalis | 0% | 0%
WP | 8 | xxx | EMBL-EBI | 0% | 0%
T | 8.1 | Profiling of existing source annotations, at-scale curation and data services | EMBL-EBI | 0% | 0%
D | 8.1 | xxx | EMBL-EBI | 0% | 0%
T | 8.2 | Data submissions tools and user workflows to capture improved sequenced material source annotations at point of deposition | EMBL-EBI | 0% | 0%
D | 8.2 | xxx | EMBL-EBI | 0% | 0%
T | 8.3 | Operation of the ELIXIR Contextual Data Clearinghouse for the reporting of source material annotation gaps and inaccuracies | UTARTU | 0% | 0%
D | 8.3 | xxx | UTARTU | 0% | 0%
T | 8.4 | Web interface for ELIXIR Contextual Data Clearinghouse [M9] | EMBL-EBI | 0% | 0%
#REF! | #REF! | xxx | #REF! | 0% | 0%
#REF! | #REF! | #REF! | #REF! | 0% | 0%
D | 8.4 | First submission and access tools available for BIOM data [M24] | EMBL-EBI | 50% | 50% | 0% | 0%
WP | 1900-01-09 | JRA-04 Delivering a trusted and evolving taxonomic framework for data integration | Sp2000 | 50% | 50% | 0% | 0%
T | 10.1 | Automated ingestion of published taxonomic information | GBIF | 50% | 50%
D | 1900-01-09 02:24 | New and updated taxonomic data products automatically visible in taxonomic framework. | GBIF | 50% | 50% | 0% | 0%
T | 10.2 | Data mapping for taxonomic information | GBIF | 50% | 50%
D | 1900-01-09 04:48 | Workflow for bi-directional linking of taxonomic references to literature [M24] | GBIF | 50% | 50% | 0% | 0%
T | 10.3 | Curation and validation of taxonomic information | Sp2000 | 50% | 50% | 0% | 0%
D | 1900-01-09 07:12 | Validation and curation workbench for taxonomic data | Sp2000 | 50% | 50% | 0% | 0%
D | 10.5 | CoL services for direct encapsulated use within search and discovery services of BiCIKL partner infrastructures [M27] | Sp2000 | 75% | 75% | 0% | 0%
WP | 1900-01-10 | JRA-05 FAIR Data Place: linking, finding and access | SIB | 75% | 75% | 0% | 0%
T | 11.1 | Benchmarking collection | Plazi | 75% | 75% | 0% | 0%
D | 1900-01-10 02:24 | Evaluation benchmark: a database of questions associated with a set of relevant articles (e.g. PMIDs) to measure the progress of the WP towards an effective search service | Plazi | 75% | 75% | 0% | 0%
T | 11.2 | Distributed search, link prediction and validation | Naturalis | 75% | 75% | 0% | 0%
D | 1900-01-10 04:48 | Search and link association services: A RESTful API, which will input a link/accession number and return a ranked list of neighbors links with a confidence score [M18] | Naturalis | 75% | 75% | 0% | 0%
T | 11.3 | Passage retrieval | SIB | 75% | 75% | 0% | 0%
D | 1900-01-10 07:12 | Passage retrieval services: A RESTful API, which will input a set of keywords and return a set of articles/passages ranked by relevance[M18] | SIB | 75% | 75% | 0% | 0%
T | 11.4 | Factoid question-answering | SIB | 75% | 75% | 0% | 0%
D | 1900-01-10 09:36 | Factoid question-answering: A RESTful API, which will input a factoid question in natural language and extract a short answer out of the articles/passages returned by D10.3 [M24] | SIB | 75% | 75% | 0% | 0%
T | 11.5 | Search and Question-Answering Portal | Plazi | 75% | 75% | 0% | 0%
D | 11.5 | Workbench implementation: a set of responsive Graphic User Interfaces developed in HTML 5.x/JavaScript to operate the aforementioned services. [M32] | Plazi | 75% | 75% | 50% | 0%
WP | 12 | Project Management | Pensoft | 75% | 75% | 50% | 0%
T | 12.1 | Detailed project planning and Standard Operational Procedures (SOP) (detailed description of governance structure & mechanisms) | Pensoft | 75% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 75% | 75% | 50% | 0%
D | 12.9 | Data Management Plan | Pensoft | 75% | 75% | 50% | 0%
T | 12.2 | Organisation of annual General Assembly and monthly Executive Board meetings | Pensoft | 75% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 75% | 75% | 50% | 0%
#REF! | #REF! | #REF! | #REF! | 75% | 75% | 50% | 0%
D | 12.1 | Project Work Plan and Standard Operational Procedures | Pensoft | 75% | 75% | 50% | 0%
D | 12.5 | Third General Assembly report | Pensoft | 75% | 75% | 50% | 0%
D | 12.6 | Internal communication platform | Pensoft | 75% | 75% | 50% | 0%
T | 12.4
D | 12.7
T | 12.5
D | 12.2
T | 9.1
#REF! | #REF!
#REF! | #REF!
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0
0
0
0

## RS1 (hidden)
Resource | Cost | Use Org Holidays | Department |  | Workhours Start | Workhours End | WorkdaySun | WorkdayMon | WorkdayTue | WorkdayWed | WorkdayThu | WorkdayFri | WorkdaySat | Holidays
Organization |  | FALSE |  | DO NOT MODIFY THIS SHEET OR INSERT COLUMNS | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Pensoft |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
ELIXIR |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Naturalis |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
MBG |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
CETAF |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
GBIF |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Plazi |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
SIB |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
EBI_EMBL |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
LifeWatch_ERIC |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
UTartu |  | TRUE |  |  | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0

## GS1 (hidden)
GCTYPE | SSN | DateFormat | WeekNumType | EC | CurrencySymbol | BaselineBudget | EstimatedBudget | ActualCosts | TotalACS | ShowOverdueBar | ShowBaselineBar | ShowActualBar | ShowCompleted | ShowInProgress | ShowPlanned | ShowLate | ShowTimelineGrid | ShowHolidays | ShowWeekends | ShowHolidaysPR | ShowWeekendsPR | ShowTodayLines | ShowDependencyConnector | ShowGrouping | ShowEstBaseBar | CurrentView | WeekStartDay | EnableBarText | BarTextCharacters | BarTextFontSize | BarTextDataColumnName | BarTextIsBold | BarTextIsItalic | BarTextIsUnderline | PercentageEntryMode | PercentageCalculationType | ProjectName | ThemeName | SelectedTheme | EBC | EMC | PCC | BBC | ABC | OBC | DLC | TLC | TBC | GBC | PBC | HBC | HC | WC | HCPR | WCPR | CR1C | CR12C | CR2C | CR3C | TGB | EBaseC | TPCH | TPCN | TPCL | TSCC | TSCI | TSCP | HCOL | DCOL | WCOL | MCOL | QCOL | HYCOL | YCOL | HWID | DWID | WWID | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | GRT | RefreshTimeline | TimelineVisible | CalcBED | CalcAED | PTDS
ds082 | 0 | DDD DD\-MMM\-YY | ISO | TRUE | € | 5.000.000,00 | 5.000.000,00 |  | 0 | FALSE | TRUE | TRUE | 1 | 1 | 1 | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 0 | 1 | M | 1 | FALSE | 20 | 9 | Task | TRUE | FALSE | FALSE | manual | simple |  | Blue | Classic | [28 empty] | 240 | 720 | 156 | 35 | 11 | 5 | 2 | 3 | 2 | 3 | 4 | 12 | 12 | 15 | TRUE | TRUE | 2021-01-01 | 2023-12-31 | 6 | 10 | 12 | 15 | TRUE | TRUE | 2019-06-01 | 2019-07-26 | RS1 | TRUE | TRUE | TRUE | TRUE | FALSE
Classic
Excel
Dark
Custom